## Summary
Active Page TypeScript Error Tracker - Complete With Resolution Notes
Total Active Pages | Original Errors
27 | 322
Current Errors | Resolved Errors
0 | 322
Resolved Pages | Pending Pages
27 | 0
Working Pages | Overall Score / 10
0 | 10
Snapshot | Verification
2026-08-13T09:14:36.543Z | Active-page filtered tsc returned 0 diagnostics

## Active Pages Complete
Page Name | Route | Path | Original Errors | Previous Error Summary | What We Resolved | Current Errors | Current Error Status / Future Reference | Status | Owner / Task | Score / 10
Login | / | D:\crm\k-crm\app\page.tsx | 0 | No previous active-page TypeScript errors in the tracked snapshot. | No code fix required for this page. | 0 | Clean. Keep this page monitored during auth/login changes because it is the public entry point. | Resolved | Coordinator | 10
Access Denied | /access-denied | D:\crm\k-crm\app\access-denied\page.tsx | 0 | No previous active-page TypeScript errors in the tracked snapshot. | No code fix required for this page. | 0 | Clean. This remains the redirect target for restricted routes. | Resolved | Coordinator | 10
Dashboard | /dashboard | D:\crm\k-crm\app\dashboard\page.tsx | 2 | 2 previous errors: User.imageUrl was read by the dashboard UI but not declared on the User type. | Added optional imageUrl to the auth User contract so existing dashboard profile image reads are typed. | 0 | Resolved. Current active-page TypeScript status: 0 errors. Future risk: keep auth user shape aligned with UI fields. | Resolved | Coordinator | 10
Leads | /leads | D:\crm\k-crm\app\leads\page.tsx | 0 | No previous active-page TypeScript errors in the tracked snapshot. | No code fix required for this page. | 0 | Clean. | Resolved | Coordinator | 10
Leads Assign | /leads/assign | D:\crm\k-crm\app\leads\assign\page.tsx | 41 | 41 previous errors: stale date literal, implicit callback any values, extra CRM fields not present on shared Lead, nullable sort values, chart percent possibly undefined, unsafe indexing. | Added local DateFilter and AssignmentLead typing, fixed thisweek to this_week, typed callbacks, guarded updatedAt fallback and nullable comparisons, aligned local extra fields used by the page. | 0 | Resolved by Task 2. Current active-page TypeScript status: 0 errors. Future reference: page intentionally uses a local enriched lead type instead of widening shared Lead globally. | Resolved | Task 2 | 10
Calls Reports | /calls/reports | D:\crm\k-crm\app\calls\reports\page.tsx | 1 | 1 previous error: Recharts Bar label formatter signature did not match LabelFormatter. | Wrapped the formatter with a local compatibility cast while preserving existing label text behavior. | 0 | Resolved. Current active-page TypeScript status: 0 errors. | Resolved | Coordinator | 10
Sales Reports | /sales/reports | D:\crm\k-crm\app\sales\reports\page.tsx | 10 | 10 previous errors: rank sort key used as SalesRow index, ExcelJS runtime import used as namespace types, and Recharts label formatter signature mismatch. | Separated rank handling before row indexing, imported ExcelJS Fill/Border types correctly, and adjusted Recharts formatter typing. | 0 | Resolved. Current active-page TypeScript status: 0 errors. Future risk: keep derived sort keys separate from raw SalesRow keys. | Resolved | Coordinator | 10
Marketing Funnel | /marketing-funnel | D:\crm\k-crm\app\marketing-funnel\page.tsx | 2 | 2 previous errors: marketing section props were mismatched; KPISection/LeadQualitySection prop expectations were crossed. | Passed filters to KPISection where required and removed the invalid filters prop from LeadQualitySection. | 0 | Resolved by Task 4. Current active-page TypeScript status: 0 errors. | Resolved | Task 4 | 10
Google PPC | /marketing/google-ppc | D:\crm\k-crm\app\marketing\google-ppc\page.tsx | 1 | 1 previous error: import path ended with .tsx while allowImportingTsExtensions is not enabled. | Changed hook import to extensionless module path. | 0 | Resolved. Current active-page TypeScript status: 0 errors. | Resolved | Coordinator | 10
Facebook PPC | /marketing/facebook-ppc | D:\crm\k-crm\app\marketing\facebook-ppc\page.tsx | 0 | No previous active-page TypeScript errors in the tracked snapshot. | No code fix required for this page. | 0 | Clean. | Resolved | Coordinator | 10
Google Adword Reports | /google-adword-reports | D:\crm\k-crm\app\google-adword-reports\page.tsx | 0 | No previous active-page TypeScript errors in the tracked snapshot. | No code fix required for this page. | 0 | Clean. | Resolved | Coordinator | 10
Villa Raag Booking FMS | /fms/bookings/villa-raag | D:\crm\k-crm\app\fms\bookings\villa-raag\page.tsx | 29 | 29 previous errors: local Booking interface did not include fields already read by the page, nullable collection metadata mismatched state, sort/payment fallbacks lacked guards, and Recharts pie label typing was incomplete. | Expanded the page-local Booking shape, added contextual typing, guarded optional values, changed nullable metadata to undefined-compatible values, widened formatCurrency input, and typed the pie label callback. | 0 | Resolved by Task 3. Current active-page TypeScript status: 0 errors. Future reference: this page now documents more of the runtime booking data shape locally. | Resolved | Task 3 | 10
KTAHV Team Booking FMS | /fms/bookings/team | D:\crm\k-crm\app\fms\bookings\team\page.tsx | 198 | 198 previous errors: largest cluster. Runtime stage objects were typed like Map<string,string> but used as keyed records, Booking fields used by the UI were missing, payment/reset state shapes were incomplete, local booking variable was used before declaration, unsupported UI props were passed, and modal callback signatures drifted. | Added page-local Booking and stage record typing, cast hook data at the page boundary, fixed sales/accounts/FO/checkout stage access, fixed handleAction and booking shadowing, added missing payment/reset fields, removed unsupported portal/modal props, and aligned modal submit callbacks to refetchBookings. | 0 | Resolved by Task 1. Current active-page TypeScript status: 0 errors. Future reference: do not reintroduce Map-style typing here unless all call sites are converted to .get/.set; current page expects keyed stage records. | Resolved | Task 1 | 10
Doctor Consultation | /doctor-consultation | D:\crm\k-crm\app\doctor-consultation\page.tsx | 5 | 5 previous errors: reduce callback parameters inferred as any and plain div elements were given invalid value props. | Typed reducer accumulator/item values and removed invalid value attributes from non-form div elements. | 0 | Resolved. Current active-page TypeScript status: 0 errors. | Resolved | Coordinator | 10
Doctor Consultation Calendar | /doctor-consultation/calendar | D:\crm\k-crm\app\doctor-consultation\calendar\page.tsx | 0 | No previous active-page TypeScript errors in the tracked snapshot. | No code fix required for this page. | 0 | Clean. | Resolved | Coordinator | 10
Doctor Consultation History | /doctor-consultation/history | D:\crm\k-crm\app\doctor-consultation\history\page.tsx | 1 | 1 previous error: Recharts pie label percent could be undefined. | Added a safe percent fallback before formatting. | 0 | Resolved. Current active-page TypeScript status: 0 errors. | Resolved | Coordinator | 10
Prescription New | /doctor-consultation/prescription/new | D:\crm\k-crm\app\doctor-consultation\prescription\new\page.tsx | 0 | No previous active-page TypeScript errors in the tracked snapshot. | No code fix required for this page. | 0 | Clean. | Resolved | Coordinator | 10
Voicecall Received Data | /voicecall/data/received | D:\crm\k-crm\app\voicecall\data\received\page.tsx | 2 | 2 previous errors: received hook rows and local enriched table rows were treated as the same type. | Typed hook rows as ReceivedLead before converting them into local ReceivedRow objects with display/status fields. | 0 | Resolved by Task 4. Current active-page TypeScript status: 0 errors. Future reference: keep API row and UI enriched row types separate. | Resolved | Task 4 | 10
Voicecall Sent Data | /voicecall/data/sent | D:\crm\k-crm\app\voicecall\data\sent\page.tsx | 2 | 2 previous errors: sent hook type did not expose _ts_num/_dt_num even though the page uses enriched timestamp fields. | Typed local sent rows as enriched rows containing _ts_num and _dt_num. | 0 | Resolved by Task 4. Current active-page TypeScript status: 0 errors. Future reference: timestamp helper fields are UI-enrichment fields. | Resolved | Task 4 | 10
Voicecall Summary | /voicecall/summary | D:\crm\k-crm\app\voicecall\summary\page.tsx | 2 | 2 previous errors: group click callback arity mismatch and calculatedstatus field not present on the typed received row. | Normalized GROUPS callback signatures and used existing/fallback qualification status fields for received modal rows. | 0 | Resolved by Task 4. Current active-page TypeScript status: 0 errors. | Resolved | Task 4 | 10
Meetings | /meetings | D:\crm\k-crm\app\meetings\page.tsx | 4 | 4 previous errors: ActionItem lacked _db_id, company select passed a free string to a union type, and delete popup could be null. | Added optional _db_id to ActionItem, cast company select values to the ActionItem company union, and guarded deleteMeeting call when delPopup is null. | 0 | Resolved. Current active-page TypeScript status: 0 errors. Future reference: saved meeting tasks may carry database ids in the client model. | Resolved | Coordinator | 10
Accounts Tracker | /accounts-tracker | D:\crm\k-crm\app\accounts-tracker\page.tsx | 7 | 7 previous errors: implicit any in getAgentColor, salesVerify.salesAgent not in typed stage, impossible status comparison with Partial, and unsafe dynamic chart-order indexing. | Typed getAgentColor inputs, used bookingTakenBy for sales owner sorting, made status union include Partial, and typed chart order as Record<string, number>. | 0 | Resolved. Current active-page TypeScript status: 0 errors. | Resolved | Coordinator | 10
MR-FMS | /MR-FMS | D:\crm\k-crm\app\MR-FMS\page.tsx | 0 | No previous active-page TypeScript errors in the tracked snapshot. | No code fix required for this page. | 0 | Clean. | Resolved | Coordinator | 10
CRR FMS | /crr-fms | D:\crm\k-crm\app\crr-fms\page.tsx | 12 | 12 previous errors: sticky table style helper inferred invalid CSSProperties and CRR modal prop contracts were too narrow for Guest and async submit handlers. | Typed frozenCellStyle as CSSProperties and updated Driver Arrival, Driver Departure, and Guest Requirement modal props to accept Guest plus async submit handlers. | 0 | Resolved. Current active-page TypeScript status: 0 errors. Future reference: CRR table sticky styles should remain React.CSSProperties-compatible. | Resolved | Coordinator | 10
Voicecall Non Qualified | /voicecall/non-qualified | D:\crm\k-crm\app\voicecall\non-qualified\page.tsx | 2 | 2 previous errors: Chart.js legend callback expected a different call signature and the chart element hidden property was not typed. | Adjusted Chart.js label generation to use supported callback/data visibility typing. | 0 | Resolved by Task 4. Current active-page TypeScript status: 0 errors. | Resolved | Task 4 | 10
FMS Pending Tasks | /fms/pending-tasks | D:\crm\k-crm\app\fms\pending-tasks\page.tsx | 0 | No previous active-page TypeScript errors in the tracked snapshot. | No code fix required for this page. | 0 | Clean. | Resolved | Coordinator | 10
FMS Enquiry Reverification | /fms/enquiry-reverification | D:\crm\k-crm\app\fms\enquiry-reverification\page.tsx | 1 | 1 previous error: Select onValueChange string callback did not match the narrower date filter state setter. | Wrapped Select onValueChange and cast value to the page date-filter union. | 0 | Resolved. Current active-page TypeScript status: 0 errors. | Resolved | Coordinator | 10

## Original Error Pages
Page Name | Route | Path | Original Errors | Previous Error Summary | What We Resolved | Current Errors | Current Error Status / Future Reference | Status | Owner / Task | Score / 10
Dashboard | /dashboard | D:\crm\k-crm\app\dashboard\page.tsx | 2 | 2 previous errors: User.imageUrl was read by the dashboard UI but not declared on the User type. | Added optional imageUrl to the auth User contract so existing dashboard profile image reads are typed. | 0 | Resolved. Current active-page TypeScript status: 0 errors. Future risk: keep auth user shape aligned with UI fields. | Resolved | Coordinator | 10
Leads Assign | /leads/assign | D:\crm\k-crm\app\leads\assign\page.tsx | 41 | 41 previous errors: stale date literal, implicit callback any values, extra CRM fields not present on shared Lead, nullable sort values, chart percent possibly undefined, unsafe indexing. | Added local DateFilter and AssignmentLead typing, fixed thisweek to this_week, typed callbacks, guarded updatedAt fallback and nullable comparisons, aligned local extra fields used by the page. | 0 | Resolved by Task 2. Current active-page TypeScript status: 0 errors. Future reference: page intentionally uses a local enriched lead type instead of widening shared Lead globally. | Resolved | Task 2 | 10
Calls Reports | /calls/reports | D:\crm\k-crm\app\calls\reports\page.tsx | 1 | 1 previous error: Recharts Bar label formatter signature did not match LabelFormatter. | Wrapped the formatter with a local compatibility cast while preserving existing label text behavior. | 0 | Resolved. Current active-page TypeScript status: 0 errors. | Resolved | Coordinator | 10
Sales Reports | /sales/reports | D:\crm\k-crm\app\sales\reports\page.tsx | 10 | 10 previous errors: rank sort key used as SalesRow index, ExcelJS runtime import used as namespace types, and Recharts label formatter signature mismatch. | Separated rank handling before row indexing, imported ExcelJS Fill/Border types correctly, and adjusted Recharts formatter typing. | 0 | Resolved. Current active-page TypeScript status: 0 errors. Future risk: keep derived sort keys separate from raw SalesRow keys. | Resolved | Coordinator | 10
Marketing Funnel | /marketing-funnel | D:\crm\k-crm\app\marketing-funnel\page.tsx | 2 | 2 previous errors: marketing section props were mismatched; KPISection/LeadQualitySection prop expectations were crossed. | Passed filters to KPISection where required and removed the invalid filters prop from LeadQualitySection. | 0 | Resolved by Task 4. Current active-page TypeScript status: 0 errors. | Resolved | Task 4 | 10
Google PPC | /marketing/google-ppc | D:\crm\k-crm\app\marketing\google-ppc\page.tsx | 1 | 1 previous error: import path ended with .tsx while allowImportingTsExtensions is not enabled. | Changed hook import to extensionless module path. | 0 | Resolved. Current active-page TypeScript status: 0 errors. | Resolved | Coordinator | 10
Villa Raag Booking FMS | /fms/bookings/villa-raag | D:\crm\k-crm\app\fms\bookings\villa-raag\page.tsx | 29 | 29 previous errors: local Booking interface did not include fields already read by the page, nullable collection metadata mismatched state, sort/payment fallbacks lacked guards, and Recharts pie label typing was incomplete. | Expanded the page-local Booking shape, added contextual typing, guarded optional values, changed nullable metadata to undefined-compatible values, widened formatCurrency input, and typed the pie label callback. | 0 | Resolved by Task 3. Current active-page TypeScript status: 0 errors. Future reference: this page now documents more of the runtime booking data shape locally. | Resolved | Task 3 | 10
KTAHV Team Booking FMS | /fms/bookings/team | D:\crm\k-crm\app\fms\bookings\team\page.tsx | 198 | 198 previous errors: largest cluster. Runtime stage objects were typed like Map<string,string> but used as keyed records, Booking fields used by the UI were missing, payment/reset state shapes were incomplete, local booking variable was used before declaration, unsupported UI props were passed, and modal callback signatures drifted. | Added page-local Booking and stage record typing, cast hook data at the page boundary, fixed sales/accounts/FO/checkout stage access, fixed handleAction and booking shadowing, added missing payment/reset fields, removed unsupported portal/modal props, and aligned modal submit callbacks to refetchBookings. | 0 | Resolved by Task 1. Current active-page TypeScript status: 0 errors. Future reference: do not reintroduce Map-style typing here unless all call sites are converted to .get/.set; current page expects keyed stage records. | Resolved | Task 1 | 10
Doctor Consultation | /doctor-consultation | D:\crm\k-crm\app\doctor-consultation\page.tsx | 5 | 5 previous errors: reduce callback parameters inferred as any and plain div elements were given invalid value props. | Typed reducer accumulator/item values and removed invalid value attributes from non-form div elements. | 0 | Resolved. Current active-page TypeScript status: 0 errors. | Resolved | Coordinator | 10
Doctor Consultation History | /doctor-consultation/history | D:\crm\k-crm\app\doctor-consultation\history\page.tsx | 1 | 1 previous error: Recharts pie label percent could be undefined. | Added a safe percent fallback before formatting. | 0 | Resolved. Current active-page TypeScript status: 0 errors. | Resolved | Coordinator | 10
Voicecall Received Data | /voicecall/data/received | D:\crm\k-crm\app\voicecall\data\received\page.tsx | 2 | 2 previous errors: received hook rows and local enriched table rows were treated as the same type. | Typed hook rows as ReceivedLead before converting them into local ReceivedRow objects with display/status fields. | 0 | Resolved by Task 4. Current active-page TypeScript status: 0 errors. Future reference: keep API row and UI enriched row types separate. | Resolved | Task 4 | 10
Voicecall Sent Data | /voicecall/data/sent | D:\crm\k-crm\app\voicecall\data\sent\page.tsx | 2 | 2 previous errors: sent hook type did not expose _ts_num/_dt_num even though the page uses enriched timestamp fields. | Typed local sent rows as enriched rows containing _ts_num and _dt_num. | 0 | Resolved by Task 4. Current active-page TypeScript status: 0 errors. Future reference: timestamp helper fields are UI-enrichment fields. | Resolved | Task 4 | 10
Voicecall Summary | /voicecall/summary | D:\crm\k-crm\app\voicecall\summary\page.tsx | 2 | 2 previous errors: group click callback arity mismatch and calculatedstatus field not present on the typed received row. | Normalized GROUPS callback signatures and used existing/fallback qualification status fields for received modal rows. | 0 | Resolved by Task 4. Current active-page TypeScript status: 0 errors. | Resolved | Task 4 | 10
Meetings | /meetings | D:\crm\k-crm\app\meetings\page.tsx | 4 | 4 previous errors: ActionItem lacked _db_id, company select passed a free string to a union type, and delete popup could be null. | Added optional _db_id to ActionItem, cast company select values to the ActionItem company union, and guarded deleteMeeting call when delPopup is null. | 0 | Resolved. Current active-page TypeScript status: 0 errors. Future reference: saved meeting tasks may carry database ids in the client model. | Resolved | Coordinator | 10
Accounts Tracker | /accounts-tracker | D:\crm\k-crm\app\accounts-tracker\page.tsx | 7 | 7 previous errors: implicit any in getAgentColor, salesVerify.salesAgent not in typed stage, impossible status comparison with Partial, and unsafe dynamic chart-order indexing. | Typed getAgentColor inputs, used bookingTakenBy for sales owner sorting, made status union include Partial, and typed chart order as Record<string, number>. | 0 | Resolved. Current active-page TypeScript status: 0 errors. | Resolved | Coordinator | 10
CRR FMS | /crr-fms | D:\crm\k-crm\app\crr-fms\page.tsx | 12 | 12 previous errors: sticky table style helper inferred invalid CSSProperties and CRR modal prop contracts were too narrow for Guest and async submit handlers. | Typed frozenCellStyle as CSSProperties and updated Driver Arrival, Driver Departure, and Guest Requirement modal props to accept Guest plus async submit handlers. | 0 | Resolved. Current active-page TypeScript status: 0 errors. Future reference: CRR table sticky styles should remain React.CSSProperties-compatible. | Resolved | Coordinator | 10
Voicecall Non Qualified | /voicecall/non-qualified | D:\crm\k-crm\app\voicecall\non-qualified\page.tsx | 2 | 2 previous errors: Chart.js legend callback expected a different call signature and the chart element hidden property was not typed. | Adjusted Chart.js label generation to use supported callback/data visibility typing. | 0 | Resolved by Task 4. Current active-page TypeScript status: 0 errors. | Resolved | Task 4 | 10
FMS Enquiry Reverification | /fms/enquiry-reverification | D:\crm\k-crm\app\fms\enquiry-reverification\page.tsx | 1 | 1 previous error: Select onValueChange string callback did not match the narrower date filter state setter. | Wrapped Select onValueChange and cast value to the page date-filter union. | 0 | Resolved. Current active-page TypeScript status: 0 errors. | Resolved | Coordinator | 10

## Task Breakdown
Task | Scope | Path / Files | Original Errors | Previous Error Summary | What We Resolved | Current Errors | Resolved Errors | Status | Score / 10 | Current Error Status / Future Reference
Task 1 | KTAHV Team Booking FMS | app\fms\bookings\team\page.tsx | 198 | 198 previous errors: Map-style stage typing, missing Booking fields, state/reset shape mismatches, booking shadowing, unsupported UI props, and modal callback drift. | Resolved page-local Booking/stage record typing, hook boundary casting, stage access, handleAction/booking shadowing, missing payment/reset fields, unsupported props, and modal submit callbacks. | 0 | 198 | Resolved | 10 | Future reference: keyed stage records are intentional for this page.
Task 2 | Leads Assign | app\leads\assign\page.tsx | 41 | 41 previous errors: stale date literal, implicit anys, extra CRM lead fields, nullable sort values, chart percent, and unsafe indexing. | Resolved local DateFilter/AssignmentLead typing, callback annotations, selectedLead fallback, and sort/null guards. | 0 | 41 | Resolved | 10 | Future reference: enriched assignment fields stay page-local.
Task 3 | Villa Raag Booking FMS | app\fms\bookings\villa-raag\page.tsx | 29 | 29 previous errors: incomplete local Booking type, nullable state metadata, sort/payment guards, and pie label typing. | Resolved by expanding local Booking interface and adding safe typing/guards around existing runtime data. | 0 | 29 | Resolved | 10 | Future reference: runtime booking fields are documented locally.
Task 4 | Marketing + Voice Pages | 5 active page files | 10 | 10 previous errors: marketing prop mismatch, voice enriched rows vs API rows, Chart.js label typing, summary row/click typing. | Resolved marketing section props, API-to-UI row conversions, Chart.js legend typing, and summary status/callback typing. | 0 | 10 | Resolved | 10 | Future reference: keep API rows and UI-enriched rows separate.
Coordinator | Smaller Active Page Fixes | dashboard, reports, accounts, CRR, doctor, meetings, enquiry | 44 | 44 previous errors across smaller active pages: auth user contract, report/chart typings, accounts status/sorting, CRR style/modal contracts, meetings task typing, select callback typing. | Resolved with targeted local type-contract fixes while preserving behavior. | 0 | 44 | Resolved | 10 | Future reference: these are type-contract fixes, not workflow behavior changes.

## Restricted Excluded
Restricted Route | Reason
/helpdesk | Excluded because route-guard sends this route to /access-denied.
/meet | Excluded because route-guard sends this route to /access-denied.
/performance | Excluded because route-guard sends this route to /access-denied.
/users | Excluded because route-guard sends this route to /access-denied.
/calls | Excluded because route-guard sends this route to /access-denied.
/fms | Excluded because route-guard sends this route to /access-denied.
/fms/bookings | Excluded because route-guard sends this route to /access-denied.
/fms/bookings/employee-wise | Excluded because route-guard sends this route to /access-denied.
/fms/bookings/new | Excluded because route-guard sends this route to /access-denied.
/fms/bookings/unverified | Excluded because route-guard sends this route to /access-denied.
/fms/bookings/verified | Excluded because route-guard sends this route to /access-denied.
/fms/doctor-consultation | Excluded because route-guard sends this route to /access-denied.
/fms/v3 | Excluded because route-guard sends this route to /access-denied.
/leads/duplicates | Excluded because route-guard sends this route to /access-denied.
/leads/duplicates/assign | Excluded because route-guard sends this route to /access-denied.
/leads/duplicates/duplicates | Excluded because route-guard sends this route to /access-denied.
/leads/duplicates_old | Excluded because route-guard sends this route to /access-denied.
/reports | Excluded because route-guard sends this route to /access-denied.
/reports/sales-conversion | Excluded because route-guard sends this route to /access-denied.
/marketing-dashboard | Excluded because route-guard sends this route to /access-denied.